## Slide 1: Bond Program Fiscal Capacity Committee
August 25, 2026

## Slide 2: Agenda
2023 GO Bond Program Status
Stages of Project Execution
Project Execution Challenges
Project Execution Resources
2023 Lessons Learned and 2028 Changes
GO Bond Programs Background

## Slide 3
The City has a long history of issuing GO bonds
Phoenix voters have approved 13 bond programs since 1957, totaling $5.1 billion
2023 GO Bond Program approved for $500M
GO Bonds were issued in 2024 (1st Tranche); next issuance planned for fall 2026 (2nd Tranche)
GO Bonds are issued for major capital infrastructure with specific legal restrictions and financial considerations.
GO Bond Program Background

## Slide 4: 2023 GO Bond Program Status

## Slide 5: 2023 GO Bond Program $500M
Voter Approved Propositions:
$214M - Enhance Community Safety through Fire, Police, Roadway and Pedestrian Infrastructure
$109M - Improve Quality of Life in Phoenix Neighborhoods
$114M - Create a Modern, Sustainable Phoenix to Live and Work
$63M - Enhance, Preserve and Increase the Supply of Affordable Housing and Senior Centers

## Slide 6: 2023 GO Bond Program $500M
14 Departments
Arts & Culture (7)
Community & Economic Dev (3)
Fire (4)
Floodplain (3)
Heat Resilience
Housing (5)
Human Services (2)
Library (3)
Environmental Programs
Parks (10)
Planning & Development (2)
Police (3)
Public Works (3)
Street Transportation (3)
City Engineer
Budget & Research
Finance
Law
Support Functions

## Slide 7: Projects Underway
Rio Reimagined Land Acquisition - $23M
Community and Economic Development will begin community engagement & concept plan development for the site.
Fire Station 15 (45th Ave and Camelback) - $21M
Opening Fall 2026
Pavement Maintenance/Storm Drain - $81M
58 projects completed or underway, and many more to come!
July-2026-GO-Bond-Status-Update.pdf

## Slide 8: Projects Underway
Arizona State University Health Technology Center- $11.9M
April 2026 Groundbreaking
Opening Fall 2028
Heat Resilience - $7.6M
Tree planting, shade structures, reflective surfaces and green stormwater infrastructure at multiple sites throughout the City.
Affordable Housing Property Preservation - $32.8M
Four Projects under construction – Eight more planned.

## Slide 9: 2023 GO Bond Program Spending
Chart: 
| 45292 | 45323 | 45352 | 45383 | 45413 | 45444 | 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931 | 45962 | 45992 | 46023 | 46054 | 46082 | 46113 | 46143 | 46174 | 46204 | 46235 | 46266 | 46296 | 46327 | 46357 | 46388 | 46419 | 46447 | 46478 | 46508 | 46539 | 46569 | 46600 | 46631 | 46661 | 46692 | 46722 | 46753 | 46784 | 46813 | 46844 | 46874 | 46905 | 46935 | 46966 | 46997 | 47027 | 47058 | 47088 | 47119 | 47150 | 47178 | 47209 | 47239 | 47270 | 47300 | 47331 | 47362 | 47392 | 47423 | 47453 | 47484
Actual Spend through July 31, 2026 | 1672.75 | 3987.75 | 6153.5 | 9868.25 | 17529.77 | 76008.52 | 100602.79 | 214236.46 | 329196.67 | 738828 | 1042159.25 | 1363501.35 | 2132816.01 | 4916506.86 | 21219029.76 | 51673929.16 | 54307059.85 | 58518201.06 | 60129829.68 | 62465465.43 | 65098245.23 | 67718442.17 | 68352071.32 | 69359968.23 | 73876394.75 | 75864047.27 | 81718785.75 | 87762393.05 | 92506725.93 | 97527390.08 | 108784897.77
Projected Remaining Spend of 1st Tranche | 108784897.77 | 115326465.724 | 121868033.678 | 128409601.632 | 134951169.586 | 141492737.54 | 148034305.494 | 154575873.448 | 161117441.402 | 167659009.356 | 174200577.31 | 180742145.264 | 187283713.218 | 193825281.172 | 200366849.126 | 206908417.08 | 213449985.034 | 219991552.988 | 226533120.942 | 233074688.896 | 239616256.85 | 246157824.804
Projected 2nd Tranche Spend | 246157824.804 | 258723225.568 | 271288626.332 | 283854027.096 | 296419427.86 | 308984828.624 | 321550229.388 | 334115630.152 | 346681030.916 | 359246431.68 | 371811832.444 | 384377233.208 | 396942633.972 | 409508034.736 | 422073435.5 | 434638836.264 | 447204237.028 | 459769637.792 | 472335038.556 | 484900439.32 | 497465840.084 | 500000000
85% Spend
1st Tranche (Est.)
$108,784,898 (43.6%)
2nd 2023 Tranche Issuance
85% Spend 2nd Tranche (Est.)

## Slide 10: Stages of Project Execution

## Slide 11: Stages of Project Execution
Planning
Feasibility
Studies
Project Assessments
Property Acquisition
Environmental
Design
Procurement
Construction
Document
(Design)
Sustainability
Efforts
Construction
Delivery
Method
Selection
Construction
Contract
Execution
Procurement
Project
Closeout
Project
Initiation
6-8 Months
12-18 Months
12-24 Months

## Slide 12: Project Execution Challenges

## Slide 13: Project Execution Challenges
Existing $12B CIP
Limited Departmental Project Delivery Experience
Limited Comparative Costs
Limited Planning Efforts associated with 2023 GO Bond
Price escalations

## Slide 14: Project Execution Challenges
Year | 2021 Inflation Factor | Actual/ Current Forecast
2022 | 7.7% | 11.5%
2023 | 2.7% | 5.2%
2024 | 2.2% | 2.2%
2025 | 2.0% | 1.2%
2026 | 1.8% | 2.8%
2027 | 2.1% | 2.6%
2028 | 2.1% | 2.4%
2029 | 2.1% | 2.2%

## Slide 15: Project Execution Resources

## Slide 16: Project Execution Resources
Monthly Meetings
Bi-Annual Meetings with CMO
Quarterly Reports (B&R)
https://www.phoenix.gov/administration/departments/budget/general-obligation-bond.html
City Managers Dashboard
https://cmpr-dashboard-phoenix.hub.arcgis.com/pages/1de04266616342a4bcd21e6f7f5dc351
Office of City Engineer (OCE)
  Procurement, Environmental, Project Management
Facility Review Committee (OCE/Public Works)
Notes: Monthly Meeting
  Monitor Progress
  Share Lessons Learned
  “Peer Pressure” towards success

## Slide 17: 2023 Lessons Learned and 2028 Changes

## Slide 18: 2023 Lessons Learned and 2028 Changes
Careful Project Selection for Consideration
Balance between programs, projects, acquisitions
Earlier Procurement Initiation
Feasibility Study Emphasis
Advance Design Efforts
Greater support to Departments
Formalized Guidance to Non-Profit Partners
Dedicated department and OCE staff for execution
Notes: Dedicated department and OCE staff for execution – SPA and Asst City Engineer

## Slide 19: 2023 Lessons Learned and 2028 Changes
Chart: 
| 47058 | 47088 | 47119 | 47150 | 47178 | 47209 | 47239 | 47270 | 47300 | 47331 | 47362 | 47392 | 47423 | 47453 | 47484 | 47515 | 47543 | 47574 | 47604 | 47635 | 47665 | 47696 | 47727 | 47757 | 47788 | 47818 | 47849 | 47880 | 47908 | 47939 | 47969 | 48000 | 48030 | 48061 | 48092 | 48122 | 48153 | 48183 | 48214 | 48245 | 48274 | 48305 | 48335 | 48366 | 48396 | 48427 | 48458 | 48488 | 48519 | 48549 | 48580 | 48611 | 48639 | 48670 | 48700 | 48731 | 48761 | 48792 | 48823 | 48853 | 48884 | 48914 | 48945 | 48976 | 49004 | 49035 | 49065 | 49096 | 49126 | 49157 | 49188 | 49218 | 49249
Actual Spend through July 31, 2026 | 1672.75 | 3987.75 | 6153.5 | 9868.25 | 17529.77 | 76008.52 | 100602.79 | 214236.46 | 329196.67 | 738828 | 1042159.25 | 1363501.35 | 2132816.01 | 4916506.86 | 21219029.76 | 51673929.16 | 54307059.85 | 58518201.06 | 60129829.68 | 62465465.43 | 65098245.23 | 67718442.17 | 68352071.32 | 69359968.23 | 73876394.75 | 75864047.27 | 81718785.75 | 87762393.05 | 92506725.93 | 97527390.08 | 108784897.77
Projected Remaining Spend of 1st Tranche | 108784897.77 | 115326465.724 | 121868033.678 | 128409601.632 | 134951169.586 | 141492737.54 | 148034305.494 | 154575873.448 | 161117441.402 | 167659009.356 | 174200577.31 | 180742145.264 | 187283713.218 | 193825281.172 | 200366849.126 | 206908417.08 | 213449985.034 | 219991552.988 | 226533120.942 | 233074688.896 | 239616256.85 | 246157824.804
Projected 2nd Tranche Spend | 246157824.804 | 258723225.568 | 271288626.332 | 283854027.096 | 296419427.86 | 308984828.624 | 321550229.388 | 334115630.152 | 346681030.916 | 359246431.68 | 371811832.444 | 384377233.208 | 396942633.972 | 409508034.736 | 422073435.5 | 434638836.264 | 447204237.028 | 459769637.792 | 472335038.556 | 484900439.32 | 497465840.084 | 500000000
Accelerate Design
Initiate Construction
Bond Issuance
Design/Feasibility
Procurement Underway or Complete
More Consistent Delivery

## Slide 20: City Engineer’s Perspective
Project Needs are not lacking
2023 GO Bond will be delivered
Intent is all 2023 GO Bond projects will be complete or nearing completion prior to 2028 GO Bond
Confident in delivery of either option for 2028 GO Bond
Notes: 2023 Needs exceeded $1.2B

## Slide 21
Notes: 2023 Needs exceeded $1.2B

## Slide 22: Questions and Additional Discussion